## Metadata (hidden)
Open
Closed
Deferred
Cancelled

## Template
|  |  | Status | Number | Percentage | Description
|  |  | 1. Wait | 0 | #DIV/0! | No Target Date
|  |  | 2. Open | 0 | #DIV/0! | On time
|  |  | 3. Flagged | 0 | #DIV/0! | Attention Required
|  |  | 4. Warning | 0 | #DIV/0! | Not on time
|  |  | 5. Closed | 0 | #DIV/0! | Closed
|  |  | Total actions | 0
Query # | Reference | Query | Clarification Obtained | Raised By | Status | Open Date | Resolution Date | Clarifired By
TEMPLATE
Note on B11: Enter the Query ID.
Note on C11: Enter the reference which describe the source e.g. DLD-pg5)
Note on D11: Write the query description which you have faced during the project duration.
Note on E11: Mentioned the result that you have obtained OR discussion update.
Note on F11: Team who has raised the Query/Issue. E.g Offshore/Onsite
Note on G11: Update the current status of the query E.g: Wait (If No Target Date mentioned) Ongoing ( If the issue/query is on track or On time) Flagged (If the issue/query required attention and action) Warning (If the issue/query raised and delayed in delivery) Finished ( If the issue/query is closed)
Note on H11: Date when the Issue/query raised.
Note on I11: Date when issue/query resolved
Note on J11: With whome the issue/query disscussed and clarified the resolution. E.g Offshore/Onsite

## INSPECTION
|  |  | Status | Number | Percentage | Description
|  |  | 1. Wait | 0 | 0% | No Target Date
|  |  | 2. Open | 17 | 100% | On time
|  |  | 3. Flagged | 0 | 0% | Attention Required
|  |  | 4. Warning | 0 | 0% | Not on time
|  |  | 5. Closed | 0 | 0% | Closed
|  |  | Total actions | 17
Query # | Reference | Query | Clarification | Raised By | Status | Open Date | Resolution Date | Clarifired By
1 | IDM | What is the CDM that to be used? In mapping sheet, The object mapping section says Order Message, Item Data Notfication and Warehousing Inbound notification. But in Field mapping, Fields are mapped to Inventory Report |  | Offshore | Open | 2018-05-09
2 | FS | What is full loading and partial loading? And where it is to be implemented in the interface? How do we know which records to be modified and deleted? |  | Offshore | Open | 2018-05-09
3 | IDM | What is meant by ***custom*** and ***extension*** field? |  | Offshore | Open | 2018-05-09
4 | FS | For the trans codification control table, the conversion values for PlantID,GMID,UD is not mentioned |  | Offshore | Open | 2018-05-09
5 | FS | What is plant ERP, SHIFT or ATHENA? |  | Offshore | Open | 2018-05-09
6 | FS | How TIBCO will receive Insepection Lot from Plant ERP/Athena and in which Format ? |  | Offshore | Open | 2018-05-09
7 | FS | Plant ERP will send data to TIBCO or TIBCO needs to Fetch data from Plant ERP? If TIBCO need to fetch then require details for that? |  | Offshore | Open | 2018-05-09
8 | FS | Frequency request is daily at what time? |  | Offshore | Open | 2018-05-09
9 | FS | Which system will take care about synchronization with other connected system while sending or fetching Insepection Lot? |  | Offshore | Open | 2018-05-09
10 | FS | CDM used by this interface is inventoryReportMessage ? |  | Offshore | Open | 2018-05-09
11 | FS | What are the filteration logic needs whule extracting Insepection Lot? |  | Offshore | Open | 2018-05-09
12 | FS | To manually trigger the intrface is there any specfic impementation logic or fully depended on Middleware implmenetaion? |  | Offshore | Open | 2018-05-09
13 | FS | In Which format TIBCO will receive or fetch data from ERP Plant like file or IDOC or XML? |  | Offshore | Open | 2018-05-09
14 | FS | Clarificaion on Rule-1 |  | Offshore | Open | 2018-05-09
15 | FS | In BusinessRules section R9-R12 the purpose and usage of control table is not very clear? |  | Offshore | Open | 2018-05-09
16 | FS | Need clear understanding from TIBCO Perspective for all Selection and BusinessRules applicable for middleware? |  | Offshore | Open | 2018-05-09
17 | FS | Sample Qunatity is not available in mapping sheet? |  | Offshore | Open | 2018-05-09
inspection
Note on B11: Enter the Query ID.
Note on C11: Enter the reference which describe the source e.g. DLD-pg5)
Note on D11: Write the query description which you have faced during the project duration.
Note on E11: Mentioned the result that you have obtained OR discussion update.
Note on F11: Team who has raised the Query/Issue. E.g Offshore/Onsite
Note on G11: Vikash Kumar: Update the current status of the query E.g: Wait (If No Target Date mentioned) Ongoing ( If the issue/query is on track or On time) Flagged (If the issue/query required attention and action) Warning (If the issue/query raised and delayed in delivery) Finished ( If the issue/query is closed)
Note on H11: Date when the Issue/query raised.
Note on I11: Date when issue/query resolved
Note on J11: With whome the issue/query disscussed and clarified the resolution. E.g Offshore/Onsite

## Dashboard
Wait
Open
Flagged
Warning
Closed
Progress Status Dashboard
inspection